## Ark 1
GANTT CHART
PROJECT TITLE | Snow XR Masseskadetriage | Original due date:
PROJECT MANAGER | Maria Rakstad | Pushed due date:
COMPANY NAME |  | Pushed due date twice or more:
DATE | 24.10 - 2023 |  | Finshed:
|  |  | Finshed late: |  |  |  | OKTOBER | [22 empty] | NOVEMBER | [20 empty] | DECEMBER | [20 empty] | JANUARY
|  |  | Finshed very late: |  |  |  | PRE-PRODUCTION | [29 empty] | PRODUCTION START
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 40 |  |  |  |  | WEEK 41 |  |  |  |  | WEEK 42 |  |  |  |  | WEEK 43 |  |  |  |  | WEEK 44 |  |  |  |  | WEEK 45 |  |  |  |  | WEEK 46 |  |  |  |  | WEEK 47 |  |  |  |  | WEEK 48 |  |  |  |  | WEEK 49 |  |  |  |  | WEEK 50 |  |  |  |  | WEEK 51 |  |  |  |  | WEEK 52 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2
ID | TITLE | ASSIGNED | DATE | DATE | IN DAYS | COMPLETE | M | T | O | T | F | M | T | O | T | F | M | T | O | T | F | M | T | O | T | F | M | T | O | T | F | M | T | O | T | F | M | T | O | T | F | M | T | O | T | F | M | T | O | T | F | M | T | O | T | F | M | T | O | T | F | M | T | O | T | F | M | T | O | T | F | M | T | W | R | F | M | T | W | R | F
1 | Compulsory Assignment 2
2023-01-01 | Write cooperation contract | Maria Rakstad | 2023-10-01 | 2023-10-10 | 9 | 100 %
2023-02-01 | Responsibility chart | Aleksander Thorset | 2023-10-05 | 2023-10-12 | 7 | 100 %
2023-03-01 | Gantt | Aleksander Thorset | 2023-10-10 | 2023-10-24 | 14 | 100 %
2023-04-01 | Personlig SWOT analysis | Everyone | 2023-10-16 | 2023-10-24 | 8 | 100 %
2023-05-01 | Write project description draft | Everyone | 2023-10-01 | 2023-10-24 | 23 | 100 %
2023-06-01 | Make a powerpoint presentation | Everyone | 2023-10-18 | 2023-10-24 | 6 | 100 %
2023-07-01 | Threat and risk analysis | Everyone | 2023-10-15 | 2023-11-04 | 20 | 0 %
2 | Pre Production
2023-01-02 | Finish the project description draft | Everyone | 2023-10-25 | 2023-11-11 | 17 | 0 %
2023-02-02 | Make a prototype in unity | Aleksander Thorset | 2023-10-25 | 2023-11-11 | 17 | 0 %
2023-03-02 | Make an asset-list | Maria og Simen | 2023-10-25 | 2023-11-11 | 17 | 0 %
2023-04-02 | Make Gamification CLD's | Aleksander Thorset | 2023-11-01 | 2023-11-15 | 14 | 0 %
2023-05-02 | Make an injury list | Everyone | 2023-11-01 | 2023-11-20 | 19 | 0 %
[5 empty] | 0 | 0 %
[5 empty] | 0 | 0 %
[5 empty] | 0 | 0 %
[5 empty] | 0 | 0 %
[5 empty] | 0 | 0 %
[5 empty] | 0 | 0 %
0 %
0 %
0 %
0 %
0 %